## Designer
Timeline | Core Objective | Key Deliverables & Action Items | Core KPI / Output
Days 1–5 | Brand Identity & Foundation Assets | Establish visual design system using #002347 Midnight Blue, #D4AF37 Champagne Gold, and #FAF9F6 Off-White. Define typography hierarchy (Cormorant Garamond & Montserrat). Create 10 core UI card templates for website & app. | Brand Kit & 10 UI Card Templates
Days 6–10 | Fabric ASMR & Texture Asset Library | Edit and export 15 high-definition (4K) 5–10 second macro video loops of fabrics (Banarasi Jamawar, Raw Silk, 9000 Micro-Velvet) highlighting Zari thread light reflections. | 15 Fabric ASMR Video Loops
Days 11–15 | Virtual Try-On & Feature Demos | Produce 5 video tutorials and screen-recorded Reels demonstrating the AI Virtual Try-On feature (photo upload to outfit swap pipeline). | 5 AI Try-On Feature Videos
Days 16–20 | Pinterest & Campaign Visuals | Design 20 Pinterest Pins and cover graphics grouped by tradition (Muslim Nikah, Sikh Anand Karaj, Hindu Sangeet, Bengali Gaye Holud) linking to PDPs. | 20 Pinterest Board Graphics
Days 21–25 | Meta Ad Creative Suite | Create 12 Meta Ad visual variations (Click-to-WhatsApp banner overlays, dynamic carousels, and visual callouts for the £50 Tailor-Fit Guarantee). | 12 Paid Ad Banners/Carousels
Days 26–30 | Asset Export & Final Handoff | Apply subtitle overlays, audio soundscapes, and export 60 finalized social media/ad assets formatted for Instagram Reels, TikTok (9:16), and Web. | 60 Master Creative Assets Delivered

## SEO & AEO
SEO & AEO Specialists Task Plan (Days 1–30)
Timeline | Core Objective | Key Deliverables & Action Items | Core KPI / Output
Days 1–5 | Keyword & Q&A Research | Conduct keyword research targeting diaspora wedding hubs (UK, USA, Canada). Map conversational search queries for ChatGPT, Claude, and Perplexity indexation. | Target Keyword & Q&A Map
Days 6–10 | Cultural Landing Page Optimization | Write On-Page SEO content and deploy structural metadata for 8 event landing pages (e.g., "Men’s Sherwani for Nikah London," "Sikh Anand Karaj Outfits USA"). | 8 Optimized Cultural Landing Pages
Days 11–15 | Database Product Tagging & Schema | Inject rich metadata into product schemas using Wedding Intelligence Engine fields (GSM, fabric, tradition, season, body type, ceremony). Implement Product and FAQPage schema. | 100% SKU Schema Coverage
Days 16–20 | AEO Conversational Guides | Draft and publish 10 Q&A styling guides optimized for LLM citations (e.g., "What stole color matches a cream Sherwani for a summer morning Nikah?"). | 10 Indexed AEO Style Guides
Days 21–25 | Technical Audit & Usability | Perform technical SEO audit focusing on mobile page load speeds, internal deep-linking from Bespoke Design Lab pages, multi-currency canonical tags, and mobile navigation. | Technical Audit Score > 90%
Days 26–30 | Off-Page Link Building & Indexing | Submit website to 25 South Asian wedding vendor directories across London, Toronto, New York, and Houston. Secure 5 guest feature links on wedding blogs. | 30 Backlinks & Directory Listings

## Social Media Handle
Social Media Handler Task Plan (Days 31–60)
Timeline | Core Objective | Key Deliverables & Action Items | Core KPI / Output
Days 31–35 | Organic Social Launch & Auto-DM Setup | Launch publishing calendar (5 Reels/TikToks/week featuring Fabric ASMR & AI Try-On). Configure automated Comment-to-DM triggers on Meta for keywords like "price," "try on," and "fabric". | 5 Posts Published; Auto-DM Active
Days 36–40 | Paid Meta Campaign Launch | Launch Meta Click-to-WhatsApp Ads targeting "Engaged" South Asians in UK/USA/Canada. Route ad leads directly into the AI Sales Agent with referral tracking. | Meta Campaign Live ($20–$40/day)
Days 41–45 | Community WhatsApp Seeding | Distribute preview catalog cards and free AI styling consultation links across 30+ regional UK, US, and Canadian South Asian WhatsApp community groups. | 30 WhatsApp Groups Seeded
Days 46–50 | Community Center Outreach & Pinterest | Publish 20 Pinterest SEO pins. Distribute digital QR code flyers to 15 South Asian community centers and wedding venues offering WhatsApp styling advice. | 15 Community Venues Reached
Days 51–55 | Groom’s Party Campaign Push | Deploy targeted messaging campaigns highlighting the Groom’s Party multi-suit portal, automated size tracking, and 10% group discount offer. | 10 Groom’s Party Outreaches/Day
Days 56–60 | Analytics, Optimization & Reporting | Review ROAS, comment DM conversion rates, and video completion metrics. Refine ad targeting angles and re-allocate budget to top-performing geographies. | Monthly Performance Report

## Designer Ideas
DESIGNER / BRANDING - DAY-WISE CREATIVE IDEAS & EXECUTION PLAN
Companion to the 'Designer' sheet (Days 1-30). Each day block lists 6 concrete ideas - a creative concept with its hook, exact format spec, and step-by-step execution. Brand palette #002347 Midnight Blue / #D4AF37 Champagne Gold / #FAF9F6 Off-White. Type: Cormorant Garamond + Montserrat.
Timeline | Core Objective | Idea # | Creative Concept | Hook / Angle | Format & Spec | Execution Steps | Suggested Tools | Expected Output
Days 1-5 | Brand Identity & Foundation Assets | 1.1 | The Midnight Thread (signature motif) | One gold thread weaves across every asset - logo, cards, ads, packaging. It becomes the thing people recognise before they read the name. Line: "Every Royal Atelier design begins with one thread." | Logo lockup + 3 motif variants (straight / loop / RA monogram); SVG + PNG 1x-2x-3x; works on Midnight, Off-White, Gold. | 1. Sketch 10 thread-line motifs by hand. 2. Vectorise the top 3 in Figma on an 8px grid. 3. Lock stroke weights at 1 / 2 / 3px so it scales. 4. Test the motif on all 3 brand colours for contrast. 5. Export SVG (web) + PNG 3 sizes (social). | Figma, Illustrator, SVGOMG | 1 logo system + 3 motif variants
|  | 1.2 | Two Voices, One Heritage (typography story) | Cormorant Garamond = the poetry of the atelier. Montserrat = the clarity of the tech. Show both in one asset so the brand feels luxury AND modern. | Type scale H1 48 / H2 32 / H3 24 / Body 16 / Caption 12; line-height 1.2 headings, 1.5 body; weights 300-700. | 1. Build the 5-step type scale in Figma Text Styles. 2. Pair Cormorant (editorial) with Montserrat (UI/labels). 3. Check glyph support for names in Urdu / Hindi / Punjabi. 4. Write CSS tokens (font, size, weight, tracking) for the dev team. 5. Publish a 1-page type specimen for the whole team. | Figma styles, Google Fonts, Type Scale | Type token sheet + specimen
|  | 1.3 | Ten Cards, Ten Ceremonies (UI card system) | Instead of 10 generic cards, make each card belong to one ceremony. The system tells a wedding story on its own. | 1080x1350 + 1080x1920; 12-column grid; gold hairline divider; product cut-out top, ceremony label bottom. | 1. Build 1 master card component with auto-layout. 2. Create variants: Nikah, Sangeet, Anand Karaj, Gaye Holud, Mehndi, Reception, Haldi, Engagement, Groom's Party, Bespoke. 3. Design a 10-icon set, one per ceremony. 4. Add placeholder copy and swap-safe text boxes. 5. Export all 10 at both aspect ratios. | Figma components, Iconify | 10 core UI card templates
|  | 1.4 | Swatch to Screen (colour proof document) | Prove the palette on real fabric - photograph gold zari against Midnight Blue so the colours feel earned, not picked. | A4 brand page + 1080x1080 digital swatch strip; include hex, RGB, CMYK and nearest RAL. | 1. Shoot 3 cloth swatches on the 3 brand colours. 2. Document hex/RGB/CMYK/RAL for each. 3. Run WCAG contrast checks on all text/background pairs. 4. Mark approved and forbidden combinations. 5. Lay out as a shareable brand page. | Camera, Figma, WebAIM contrast checker | Colour story page + swatch strip
|  | 1.5 | The GBP 50 Seal (trust badge system) | Turn the Tailor-Fit Guarantee into a small gold seal that appears everywhere - it removes risk in one glance. | Circular seal + horizontal lockup; 3 sizes; light and dark variants. | 1. Sketch 5 seal concepts (crest, stamp, wax-seal, ribbon, monogram). 2. Pick 1 and vectorise it cleanly. 3. Build light/dark + 3-size variants. 4. Add it to the card master as a corner stamp. 5. Drop it into all 10 card templates for consistency. | Illustrator, Figma | Guarantee badge set (6 files)
|  | 1.6 | Grid of Nine (launch blueprint) | Plan the first 9 Instagram posts before publishing a single one - so the profile looks designed on day one. | 3x3 grid mock, 1080x1080 per tile; alternate product / typography / macro-detail. | 1. Map the 10 card templates onto 9 grid slots. 2. Alternate product shots with typography and detail crops. 3. Lock the exact posting order. 4. Note caption angle for each tile. 5. Get founder sign-off before any post goes live. | Figma, Canva | Grid blueprint + posting order
Days 6-10 | Fabric ASMR & Texture Asset Library | 2.1 | Zari in Motion | A light sweep across Banarasi Jamawar makes the gold zari flare and fade. Pure luxury with no words needed. | 4K 3840x2160; 120fps slowed to 24/30; 5-10s seamless loop; 90mm macro. | 1. Mount fabric flat, no wrinkles. 2. Rake a flicker-free LED at 45 degrees. 3. Shoot 120fps, sweep light or slide camera slowly. 4. Speed-ramp in post, match first/last frame for a clean loop. 5. Grade to protect gold highlights. | 90-100mm macro, tripod/slider, LED panel, Resolve | 3 x 4K zari loops
|  | 2.2 | Velvet Breath | 9000 Micro-Velvet under raking light - the pile rises and falls like it is breathing. Oddly calming. | 4K macro; shallow depth of field f/2.8; 5-8s loop; dust-free set. | 1. Brush the pile in one direction. 2. Light from a low angle so pile shadow does the work. 3. Breathe on the fabric or use a soft air puff to animate pile. 4. Shoot 3 takes at different speeds. 5. Pick the most hypnotic take. | Macro lens, air blower, LED | 3 x velvet texture loops
|  | 2.3 | Rain of Gold | Fine gold particles drift down onto Raw Silk. Slow motion makes it feel like an heirloom being revealed. | 4K 120fps; dark background; 5-10s loop. | 1. Set Midnight Blue backdrop for gold to pop. 2. Drop silk dust / fine gold flake from height. 3. Shoot at 120fps side-lit. 4. Grade to lift only the gold specks. 5. Loop by fading the last frame into the first. | Macro lens, LED, Resolve | 3 x particle loops
|  | 2.4 | Karigar's Hands | An artisan's hand glides across the fabric. One human touch turns a product video into a heritage film. | 4K, 24fps cinematic; framed to hands only, face optional; 6-10s. | 1. Brief the karigar to move slowly and naturally. 2. Frame tight on hands and thread only. 3. Light softly to flatter skin tone. 4. Capture 4-5 passes of the same gesture. 5. Grade warm, keep it documentary-real. | 50mm/85mm lens, softbox | 3 x heritage hand loops
|  | 2.5 | Thread Pull (satisfying reveal) | Pull a single zari thread and the whole weave tightens. Instantly communicates density and quality. | 4K, 120fps, extreme macro; 5s loop; clean audio. | 1. Separate one zari thread with a needle. 2. Frame extreme close so the weave fills the screen. 3. Pull slowly on camera at 120fps. 4. Capture the thread-snap sound separately. 5. Cut to loop the pull repeatedly. | Macro + extension tube, needle, mic | 2 x weave-reveal clips
|  | 2.6 | Sound Bed Library | Great ASMR is 50% audio. Build a reusable bed of fabric sounds so every future reel feels consistent. | 5 stereo beds, 30-60s each, 48kHz WAV, normalised to -14 LUFS. | 1. Record needle, scissors, thread snap, fabric brush, coin tumble. 2. Layer 2 sounds per bed. 3. Clean noise and normalise loudness. 4. Export WAV for editing + MP3 for social. 5. Name and store in one shared folder. | Shotgun mic / recorder, Audition, Resolve Fairlight | 5 reusable ASMR audio beds
Days 11-15 | Virtual Try-On & Feature Demos | 3.1 | Selfie to Sherwani in 30 Seconds | A timer overlay races through the whole journey. Speed = proof the feature is effortless. | 9:16 1080x1920; 30-45s; on-screen timer; burned-in captions. | 1. Storyboard 6 beats (upload, crop, pick, swap, adjust, share). 2. Screen-record each step at 1080x1920. 3. Add a running timer and step chips. 4. Cut on the beat, caption every step. 5. End-card: "Try it on - WhatsApp us." | OBS, Premiere/CapCut, phone screen record | 1 hero feature reel
|  | 3.2 | One Sherwani, Three Body Types | The same outfit on three different builds. Answers the quiet fear every online buyer has. | Split-screen 9:16; 30s; label each panel (size/height). | 1. Pick one best-selling sherwani. 2. Run the try-on for 3 builds/sizes. 3. Build a vertical split-screen layout. 4. Label each panel with size and height. 5. Caption: "Made to fit, not made to guess." | Try-on pipeline, CapCut, Figma overlay | 1 inclusivity demo reel
|  | 3.3 | Try Before You Fly | Speaks straight to diaspora buyers - see it on yourself before spending on international shipping and returns. | 9:16; 20-30s; diaspora angle; UK/USA/Canada framing. | 1. Write the hook in the first 2 seconds. 2. Show a return parcel as the "problem" shot. 3. Cut to the try-on as the "solution". 4. Show price + shipping in local currency. 5. CTA: send photo on WhatsApp. | CapCut, screen record, stock b-roll | 1 diaspora pain-point reel
|  | 3.4 | The Doubt-to-Decision | Emotional before/after - an unsure face scrolling alone, then a confident full look. Sells the feeling, not the feature. | 9:16; 25s; 2-act structure; soft soundscape. | 1. Film act 1: uncertain scroll, dim light. 2. Film act 2: confident reveal in full outfit. 3. Match the cut to the music swell. 4. Add a text overlay of the customer's hesitation. 5. End on the guarantee seal. | Camera, CapCut, sound library | 1 emotional brand reel
|  | 3.5 | 60-Second UI Walkthrough | A calm, no-hype tutorial for the people who want to know exactly how it works before they try. | 9:16 screen-record; 60s; numbered chips; cursor highlight. | 1. Script 5 numbered steps. 2. Record the UI cleanly with a cursor highlight. 3. Add numbered chips and a progress bar. 4. Narrate in plain language (no jargon). 5. Pin as a saved tutorial + post to YouTube Shorts. | OBS, CapCut, voice-over | 1 evergreen tutorial
|  | 3.6 | First Reaction (UGC style) | A real person, real phone, real reaction. The least "ad-like" video you can publish. | 9:16 phone-shot; 20-30s; raw, unpolished look. | 1. Ask a friend/team member to try it once, no rehearsals. 2. Film their genuine reaction on a phone. 3. Keep the natural audio. 4. Add minimal captions only. 5. Post as-is to keep the authentic feel. | Phone, CapCut | 1 UGC reaction asset
Days 16-20 | Pinterest & Campaign Visuals | 4.1 | 5 Pins x 4 Traditions | A simple maths that guarantees coverage - 5 pins each for Nikah, Anand Karaj, Sangeet and Gaye Holud. | 1000x1500 (2:3) each; 4 boards; 20 pins total. | 1. Create one board per tradition. 2. Design 5 pin layouts (product, formula, palette, mood, text). 3. Apply the layout set to each tradition. 4. Write keyword-first titles and descriptions. 5. Schedule the 20 pins across the boards. | Figma, Pinterest scheduler | 20 tradition pins
|  | 4.2 | Colour Story Pins | Pin the palette itself - Anand Karaj in gold and maroon, Gaye Holud in turmeric yellow. People save palettes for their own weddings. | 1000x1500; 4-5 colour chips per pin; hex labels optional. | 1. Research authentic ceremony palettes. 2. Turn each into a 4-5 chip palette pin. 3. Place a matching fabric swatch beside each chip. 4. Add a caption suggesting a coordinating outfit. 5. Link to the matching PDP. | Figma, Coolors | 4 palette pins
|  | 4.3 | Outfit Formula Pins | Give a rule, not a product: "Sangeet formula = 3 colours + 1 statement piece." Formulas get saved and re-shared. | 1000x1500; bold formula headline top; 3 product cut-outs below. | 1. Write 4 formulas (one per ceremony). 2. Choose 3 products that satisfy each formula. 3. Lay out with the formula text as the hero. 4. Add a small numbered key under each product. 5. Link all products to their PDPs. | Figma, Canva | 4 formula pins
|  | 4.4 | Mood Board Pins | Blend a real wedding ambience shot with a clean product cut-out - sells the occasion, not just the garment. | 1000x1500; 60% visual / 40% text; brand footer strip. | 1. Collect licensed ambience shots per tradition. 2. Cut out the hero garment cleanly. 3. Compose mood above, product below. 4. Keep text to a single line + brand footer. 5. Export and pin to the matching board. | Figma, Photoshop, stock library | 4 mood board pins
|  | 4.5 | Text-Overlay SEO Pins | A big, readable text overlay is what actually gets clicked on Pinterest - pair the keyword with a strong image. | 1000x1500; text in the middle safe zone; high contrast in brand palette. | 1. Pull 4 high-intent keywords from the SEO sheet. 2. Design 4 overlay layouts with big type. 3. Keep the text inside the safe zone. 4. Write titles/descriptions using the same keywords. 5. Add UTM-tagged links to PDPs. | Figma, keyword list from SEO & AEO sheet | 4 keyword pins
|  | 4.6 | Groom's Party Pins | Nobody designs for the groom's squad. Coordinate 5-10 looks in one pin and own the search. | 1000x1500; 5-10 coordinated looks in a grid; group-discount callout. | 1. Build 3 coordinated party palettes. 2. Design a grid pin per palette. 3. Add the group discount callout. 4. Link to the Groom's Party portal. 5. Pin to a dedicated "Groom's Squad" board. | Figma, Canva | 3 group-look pins
Days 21-25 | Meta Ad Creative Suite | 5.1 | Guarantee-First Static | Lead with the GBP 50 Tailor-Fit Guarantee as the headline, not the product. Removes the risk before anything else. | 1080x1080 + 1080x1920 + 1200x628; seal top-right; text inside safe zones. | 1. Put the guarantee seal as the visual anchor. 2. Write 3 headline variants around "fit" and "risk". 3. Keep all text out of the top/bottom 14% safe zone. 4. Export all 3 sizes per variant. 5. Set Click-to-WhatsApp as the CTA. | Figma, Meta Ads Manager | 3 static variants
|  | 5.2 | Ceremony Carousel | One carousel that walks through Nikah, Sangeet, Anand Karaj and Reception - the buyer self-selects their card. | 4 cards, 1080x1080; first card = hook; last card = CTA + guarantee. | 1. Write one card per ceremony. 2. Design a consistent template with a moving accent. 3. Order the cards by audience size. 4. Add a CTA card at the end. 5. Write primary text that mirrors the sequence. | Figma, Meta Ads Manager | 2 carousel sets
|  | 5.3 | Dynamic Product Carousel | Show people the exact outfits they already browsed - retargeting that feels helpful, not creepy. | 1080x1080; catalogue-linked; 4-6 products per user. | 1. Ensure the product catalogue feed is clean. 2. Build 3 carousel card templates. 3. Connect the dynamic creative to the catalogue. 4. Exclude purchasers from the retargeting set. 5. Pair with a "still deciding?" primary text. | Meta catalogue, Figma templates | 1 dynamic carousel set
|  | 5.4 | 6-Second Try-On Ad | The try-on IS the hook. No voice-over, no intro - the swap happens in the first frame. | 1080x1080 + 1080x1920; 6s; looped; captions only. | 1. Cut straight to the swap, no intro frame. 2. Keep it exactly 6 seconds. 3. Add 3 short caption lines max. 4. Make it seamless-loop so it reads as a GIF. 5. Test against the guarantee static. | CapCut, Premiere | 2 video ad variants
|  | 5.5 | Price-Anchor Ad | "Wedding-ready from GBP ___" sets the expectation straight away and filters in serious buyers. | 1080x1080 + 1200x628; price as hero; product lower third. | 1. Verify the entry price across currencies. 2. Design with the price as the largest element. 3. Add a small "includes tailoring" footnote. 4. Keep the guarantee seal for support. 5. Target colder audiences with this one. | Figma, Meta Ads Manager | 2 price-anchor variants
|  | 5.6 | WhatsApp Chat Mock | A mock chat screenshot that shows a real conversation ending in an outfit choice - primes the Click-to-WhatsApp behaviour. | 1080x1920; realistic chat bubbles; ends on the CTA button. | 1. Script a realistic 6-message exchange. 2. Design it in-brand, clearly stylised (not a fake screenshot scam look). 3. End the last bubble with the CTA. 4. Add "or slip into our DMs" as a soft alternative. 5. Run it against a non-chat creative to compare. | Figma, Meta Ads Manager | 1 chat-mock creative
|  | 5.7 | Countdown Ad | "X days to your function" turns a wedding date into urgency - built for the peak season months. | 1080x1080; dynamic date text; minimal layout. | 1. Identify the 3 biggest wedding months. 2. Build a layout with a large dynamic day count. 3. Add a tailoring-turnaround line. 4. Schedule it to peak 3-4 weeks before the season. 5. Refresh the number weekly. | Figma, Meta Ads Manager | 3 seasonal variants
|  | 5.8 | Testimonial Card | A real customer quote over their real photo beats any stock model shot. | 1080x1080; quote as hero; name + city + garment label. | 1. Collect 5 usable customer quotes with permission. 2. Pair each with the customer's own photo. 3. Set the quote as the largest element. 4. Add name, city and garment as small labels. 5. Rotate the best performer monthly. | Figma, customer photo library | 5 testimonial creatives
Days 26-30 | Asset Export & Final Handoff | 6.1 | One Master, Many Formats | Stop exporting by hand. One master timeline becomes every required size automatically. | Master 4K 16:9; outputs 1080x1920 (9:16), 1080x1080 (1:1), 1920x1080 (16:9), web MP4 + WebM. | 1. Build one master edit at 4K. 2. Create export presets for each ratio in Premiere/Resolve. 3. Keep titles inside a centred safe zone so crops work. 4. Batch-export all sizes from the master. 5. Name every file with the convention below. | Premiere / Resolve, Media Encoder | Export preset pack
|  | 6.2 | Caption Style Tokens | Three subtitle styles, used consistently, make 60 assets feel like one brand instead of sixty. | Royal Gold, Clean White, Festive - each with fixed font, size, position and animation. | 1. Design the 3 caption styles. 2. Save each as a reusable preset in the editor. 3. Map styles to asset types (ASMR = Clean, ads = Royal Gold). 4. Check readability on mobile at small size. 5. Document the mapping in the handoff sheet. | Premiere/CapCut presets, Figma | 3 caption style presets
|  | 6.3 | Soundscape Kits | Audio is the fastest way to make a batch of assets feel expensive. Three beds cover everything. | Royal, Soft, Festive - 3 licensed beds, 60s each, -14 LUFS. | 1. License 3 music beds that match the brand tone. 2. Normalise all to -14 LUFS. 3. Map each bed to an asset category. 4. Create 5s and 15s stings from each. 5. Store in the shared audio folder. | Artlist/Epidemic, Audition | 3 soundscape kits + stings
|  | 6.4 | Naming Convention | A filename that explains itself saves hours later - and stops "final_final_v3" forever. | RA_2026_D06_ASMR_ZariInMotion_9x16_v1.mp4 | 1. Agree the pattern: Brand_Year_DayBlock_Type_Name_Ratio_Version. 2. Write it at the top of the handoff sheet. 3. Apply it to every existing file. 4. Add a folder tree that matches (by type, then ratio). 5. Enforce it in the QC check. | Google Drive / Notion doc | Naming standard + folder tree
|  | 6.5 | Handoff Playbook | A one-page doc that lets anyone on the team publish without messaging you first. | Folder structure, specs table, caption mapping, posting order, do/don't list. | 1. Write a 1-page delivery note. 2. Include the specs table (size, ratio, loudness, duration). 3. Include the caption and sound mapping. 4. List the posting order for week one. 5. Add a do/don't list and store it at the folder root. | Notion / Google Docs | 1-page handoff playbook
|  | 6.6 | QC Gate Checklist | Nothing ships until it passes the gate - this is what keeps 60 assets clean instead of messy. | 10-point checklist run on every asset before delivery. | 1. Check safe zones and mobile crop. 2. Verify loudness at -14 LUFS and no audio clipping. 3. Confirm captions are burned in and readable. 4. Confirm the hook lands in the first 2 seconds. 5. Check brand colours and logo clearance, then sign off each asset. | Checklist in Notion, Resolve/MediaInfo | QC checklist + signed asset log
BRAND QUICK REFERENCE
Palette | #002347 Midnight Blue ¦ #D4AF37 Champagne Gold ¦ #FAF9F6 Off-White
Typography | Headings: Cormorant Garamond ¦ UI + Body: Montserrat
Hero Fabrics | Banarasi Jamawar, Raw Silk, 9000 Micro-Velvet (macro + zari light reflections)
Audience | South Asian diaspora wedding buyers - UK, USA, Canada
Ceremonies | Muslim Nikah, Sikh Anand Karaj, Hindu Sangeet, Bengali Gaye Holud
Key USP | AI Virtual Try-On ¦ GBP 50 Tailor-Fit Guarantee ¦ Groom's Party multi-suit portal
Export Rules | 9:16 1080x1920 for Reels/TikTok ¦ 1:1 1080x1080 for feed ¦ audio at -14 LUFS

## Easy Ideas (n8n)
EASY IDEAS - KYA BANANA HAI (n8n AUTOMATION READY)
Simple list for the Designer / branding weeks. Har row mein: kya banana hai, kitne, kis size mein, aur n8n ke liye ready prompt jo seedha AI node mein paste ho jaye.
Day Block | # | Kya Banana Hai (Asset) | Qty | Format / Size | Simple Idea (1 line) | n8n Prompt / Input (copy-paste) | Publish / Use
Day 1-5 | 1.1 | Logo reveal post | 1 | 1080x1350 | Pehla post: brand ka logo aur naam. | Make a 1080x1350 post. Midnight Blue #002347 background, gold #D4AF37 logo centre, text 'Royal Atelier' in Cormorant Garamond. | Instagram + Facebook
| 1.2 | Brand colour post | 1 | 1080x1350 | 3 rang jo brand ki pehchaan hain. | Make a post showing 3 colour blocks: #002347, #D4AF37, #FAF9F6 with hex code under each. | Instagram + Facebook
| 1.3 | Typography post | 1 | 1080x1350 | Fonts ka simple showcase. | Make a post with a big 'Aa' in Cormorant Garamond and Montserrat, text 'Heritage meets Modern'. | Instagram
| 1.4 | Coming soon teaser reel | 1 | 9:16, 5 sec | Launch se pehle hype. | Make a 5 sec 9:16 clip: gold thread draws across dark blue, 'Coming Soon' fades in, soft music. | Reels + TikTok
| 1.5 | Highlight covers | 5 | 1080x1920 | Nikah, Sangeet, Sherwani, Reviews, Contact. | Make 5 matching highlight covers: gold icon on Midnight Blue, labels: Nikah, Sangeet, Sherwani, Reviews, Contact. | Instagram highlights
| 1.6 | WhatsApp profile + status | 1 + 3 | 1080x1080 | WhatsApp bhi brand jaisa lage. | Make 1 square WhatsApp DP with logo and 3 status images using the brand colours. | WhatsApp Business
Day 6-10 | 2.1 | Banarasi close-up clip | 3 | 9:16, 7 sec | Zari ki chamak dikhao. | Make 3 clips of 7 sec each: slow zoom on Banarasi Jamawar, gold zari shimmer, calm music, no text. | Reels + TikTok
| 2.2 | Raw Silk close-up clip | 3 | 9:16, 7 sec | Silk ka fall aur softness. | Make 3 clips of 7 sec: raw silk draping slowly, cream colour, calm ambient music. | Reels + TikTok
| 2.3 | Velvet close-up clip | 3 | 9:16, 7 sec | Velvet ka texture. | Make 3 clips of 7 sec: macro view of 9000 Micro-Velvet, light sweep across surface, deep colour. | Reels + TikTok
| 2.4 | Fabric carousel post | 3 | 1080x1350 x5 | Ek fabric ke 5 angles. | Make a 5-slide carousel per fabric: full fabric, close-up, thread detail, colour swatch, final product. | Instagram carousel
| 2.5 | Fabric clip + 1 line text | 3 | 9:16, 10 sec | Clip pe sirf ek line likho. | Take the fabric clip and add text overlay: 'Made to be felt, not just seen.' | Reels + TikTok
| 2.6 | Quote post on fabric bg | 5 | 1080x1080 | Fabric background + quote. | Make 5 quote posts: fabric texture background + one short line of text in gold. | Instagram + Pinterest
Day 11-15 | 3.1 | Before / after try-on reel | 5 | 9:16, 15 sec | Selfie vs final outfit. | Make a 15 sec reel: left customer selfie, right AI try-on result, text 'See it on you in 30 seconds', clean music. | Reels + TikTok
| 3.2 | Screen recording demo | 3 | 9:16, 30 sec | App kaise use karein. | Show screen flow: upload photo, choose outfit, see result. Add simple step text 1-2-3. | Reels + TikTok
| 3.3 | 1 person, 3 outfits | 3 | 9:16, 20 sec | Ek hi banda, 3 looks. | Make a reel: same person in 3 different outfits, quick cuts, labels Nikah / Sangeet / Reception. | Reels + TikTok
| 3.4 | Try-on carousel | 3 | 1080x1080 x5 | 5 try-on results ek saath. | Make a 5-slide carousel of try-on results, one short caption on each slide. | Instagram carousel
| 3.5 | Feature explainer short | 3 | 9:16, 20 sec | Feature simple words mein. | Make a 20 sec explainer: 3 text slides + try-on clip, only 3 steps, no jargon. | Reels + TikTok
| 3.6 | Try-on + guarantee end card | 3 | 9:16, 15 sec | Trust dikhao. | Add text end-card 'GBP 50 Tailor-Fit Guarantee' at the end of the try-on clip. | Reels + paid ads
Day 16-20 | 4.1 | Pinterest pins - Nikah | 5 | 1000x1500 | Nikah ke looks. | Make 5 vertical pins: Nikah sherwani photo, gold and maroon colours, title text 'Nikah Sherwani - London'. | Pinterest (link to PDP)
| 4.2 | Pinterest pins - Anand Karaj | 5 | 1000x1500 | Anand Karaj ke looks. | Make 5 vertical pins: Sikh wedding outfit, royal gold colours, title text 'Anand Karaj Outfit - USA'. | Pinterest (link to PDP)
| 4.3 | Pinterest pins - Sangeet | 5 | 1000x1500 | Sangeet ke looks. | Make 5 vertical pins: Sangeet outfit, bright colours, title text 'Sangeet Outfit Ideas - UK'. | Pinterest (link to PDP)
| 4.4 | Pinterest pins - Gaye Holud | 5 | 1000x1500 | Gaye Holud ke looks. | Make 5 vertical pins: Bengali wedding outfit, turmeric yellow colours, title text 'Gaye Holud Outfit - Canada'. | Pinterest (link to PDP)
| 4.5 | Festival greeting posts | 5 | 1080x1080 | Eid, Diwali, Baisakhi, Durga Puja, Onam. | Make 5 greeting posts in brand colours, one per festival, with the festival name in English and gold text. | Instagram + Facebook
| 4.6 | Outfit of the day post | 10 | 1080x1350 | Roz ek outfit post. | Make 10 OOTD posts: one outfit photo, outfit name, one short caption line. | Instagram feed
Day 21-25 | 5.1 | Guarantee static ad | 4 | 1080x1080 | Risk hata do. | Make 4 static ads: big text 'GBP 50 Tailor-Fit Guarantee', product photo, gold seal, WhatsApp button. | Meta Click-to-WhatsApp
| 5.2 | Ceremony carousel ad | 4 | 1080x1080 x4 | Char ceremonies, char cards. | Make a 4-card carousel: Nikah, Sangeet, Anand Karaj, Reception, plus last card with WhatsApp CTA. | Meta carousel ad
| 5.3 | 6 second video ad | 4 | 9:16, 6 sec | Fast hook, no intro. | Make a 6 sec ad: try-on swap happens in the first frame, captions only, end card with CTA. | Meta Reels ad
| 5.4 | WhatsApp CTA ad | 4 | 1080x1080 | Chat pe le aao. | Make 4 ads with text 'Send us your photo on WhatsApp' and a simple chat-style visual. | Meta Click-to-WhatsApp
| 5.5 | Retargeting carousel | 4 | 1080x1080 | Jo dekh chuke hain unhe dikhao. | Make a carousel of popular outfits with text 'Still deciding? Your size is waiting.' | Meta retargeting
| 5.6 | Price ad | 4 | 1080x1080 | Price clear kar do. | Make 4 ads where the biggest text is 'Wedding-ready from GBP ___' with product below. | Meta cold audience
Day 26-30 | 6.1 | Resize all assets | All | 9:16, 1:1, 16:9 | Ek asset, teen sizes. | Batch resize every approved asset to 9:16, 1:1 and 16:9, keep same filename. | n8n batch step
| 6.2 | Add captions to videos | All videos | Burned-in | Bina sound bhi samajh aaye. | Auto-caption every video and burn subtitles in the brand font, white text with gold highlight word. | n8n + editor
| 6.3 | Add music to videos | All videos | -14 LUFS | Har video pe ek music bed. | Attach the licensed music bed to every video and normalise audio to -14 LUFS. | n8n + editor
| 6.4 | Auto-schedule in n8n | All | 1 post/day | Post khud chali jaye. | In n8n: pick one asset per day per platform from the approved folder and auto-post at 7 PM local. | n8n schedule
| 6.5 | Save to Drive folders | All | Folder tree | Sab kuch ek jagah mile. | Save finals in Drive: /Assets/{Type}/{Size}/ with filename RA_2026_DayBlock_Name. | Google Drive
| 6.6 | Weekly report | 1 | Google Sheet | Kya chala, kya nahi. | Every Monday, n8n writes views, saves, comments and DMs per post into one sheet. | n8n + Sheets
QUICK NOTES
Kaise use karein | Har row = ek asset. Right side ka n8n prompt seedha AI node mein paste kar dein.
Qty ka matlab | Kitne assets generate karne hain us day block mein.
Colours | #002347 Midnight Blue ¦ #D4AF37 Champagne Gold ¦ #FAF9F6 Off-White
Fonts | Headings: Cormorant Garamond ¦ Body + UI: Montserrat
Video ke liye | Hamesha 9:16 1080x1920 banayein (Reels + TikTok dono chal jata hai).
Audio | -14 LUFS normalise karein, warna Instagram volume gira deta hai.
Gold rule | Ek asset mein sirf ek kaam: ya brand, ya product, ya try-on. Mix na karein.